## Sheet1
Task | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Develop schedule | X
Populate provider portal front end tasks | X
Submit project implementation plan | X
Populate patient portal front end tasks | X
Populate FHIR tasks | X
Populate provider portal charting tasks | X
Provider portal: design BDRS Questionnaire resource |  | X
Patient portal: design mood Questionnaire resource |  | X
Provider portal: design BDRS questionnaire front end |  | X
Patient portal: design mood questionnaire front end |  | X
Provider portal: write QuestionnaireResponse to FHIR server |  |  | X
Patient portal: write QuestionnaireResponse to FHIR server |  |  | X
Generate QuestionnaireResponse 'history': provider BDRS data |  |  | delayed | X
Generate QuestionnaireResponse 'history': patient mood data |  |  | X
Provider portal: add button to populate generated data |  |  | X | early
Provider portal: read historical QuestionnaireResponse data |  |  |  | X
Provider portal: chart mood and BDRS data independently |  |  |  | X
Provider portal: align displays of BDRS and mood data by date/time |  |  |  |  | X
Complete final documentation |  |  |  |  | X
Complete final presentation and other deliverables |  |  |  |  | X